## Timeline
Defend Our Future Event Planning Timeline
NAME:
DATE:
GOAL(S) OF EVENT:
INVITEES:
| TIMELINE | STATUS | NOTES
Initial Logistics
Determine event date | 1 month before
Secure guests and participants | 1 month before
Secure venue | 1 month before
Determine budget (if applicable) | 1 month before
Determine invitees | 1 month before
Invitees and Invitations
Draft invitation text | 1 month before
Pull list of invitees | 1 month before
Create invitee tracking document (see example) | 3 weeks before
Send invitation | 2-3 weeks before
Share invitee tracking document to relevant stakeholders | post-invitation
Update RSVP tracking | Daily
Send reminder invitation to people who have not RSVP'd | 2 weeks before
Pre-Event Prep
Send event reminder email to 'Accepted' attendees | 1 week before
Confirm venue and catering (if applicable) | 1 week before
Prepare research for attending staff (who is coming, where they work, what they are working on - see example) | 2-4 days before
Prepare name tags (bring extra with a sharpie) | 1-2 days before
Print attendance list for tracking | 1-2 days before
Day of Event
Arrive 60 minutes before | Day of event
Touch base with venue staff - clarify any specifics (budget, space, etc.) | Day of event
Set up name tags and attendance tracking doc | Day of event
Photos - take them! | Day of event
Follow-Up
Share attendance tracking - invite them to flag personal follow up | Day after event
Send follow up 'thank you' email to all other attendees | Day after event
Complete Post-Event Report tab | Day after event
Report out (if applicable) | Next team call

## Attendance Tracking
Event Title
[DATE] |  |  |  |  | Status
[LOCATION] |  |  |  |  | Accepted
[TIME] |  |  |  |  | Attended
No Response
Invited by | RSVP | First Name | Last Name | Email | Current Organization | Current Title | Current Location | Attended

## Event Flow
Sample Event Flow - Defend Our Beer Event
GUIDE | EXAMPLE
Name of Event | Defend Our Beer
Purpose of Event | To highlight the impacts of climate change on water and beer quality.
Week day, Month, Day, Year | Thursday, December 7, 2017
Time of Event | 5:30-7:30 PM
Location Name (Linked) | Odell Brewing Company
Location Street | 800 E Lincoln Avenue
City, State Zip | Fort Collins, CO 80524
Defend Contacts at event | Defend Contacts at Event:
Cell phone numbers | John Doe – 000-000-0000 (c)
Email addresses | john@defendourfuture.org
Time/Task | 16:45 | Defend Our Future staff report to set-up:
Staff member on point |  | STAFF: John
| 5:15 – 5:30 PM | Guests check-in and mingle. Beer is available.
STAFF: John
| 5:30-6:30 PM | John welcomes panelists.
|  | - | Panelists discuss their efforts to reduce their operations' environmental footprint.
|  | - | John facilitates Q&A
STAFF: John
| 6:30-7:30 PM | Panelists and attendees mix and mingle. Beer samples are available.
| 19:30 | Event concludes. Event Concludes. Staff and participants must leave establishment by 8:00 pm.

## Budget and What to Bring
Budget (optional) |  |  |  | What to bring with you
Item | Projected | Actuals | Notes | Item | Notes
Food | 0 | 0 |  | Name Tags | Pre-print or hand-written If you have people write their own, provide an example Name CC Year - CC Host Org
Alcohol | 0 | 0 |  | Sharpies
Tour | 0 | 0 |  | Printed RSVP list for sign in
Speaker | 0 | 0 |  | Pens | Always good to have
Total | 0 | 0 |  | Camera | Take pictures or designate staff or volunteers to take pictures
|  |  |  | Drink tickets | Use if you don't think the bar can manage this

## Post-Event Report
Post-Event Report
EVENT TITLE: Example: Defend Our Beer
DATE, TIME, PLACE: Example: December 7, 2017, 5:30 - 7:30 pm, Odell Brewery Company, Fort Collins, CO
GOAL OF EVENT: Example: Bring together local breweries and students for a conversation on climate change and solutions.
INVITEES Example: Students, faculty, local organizations in the Fort Collins area
Metrics | Description of the event
Total Attendees | How did it go? What happened? Was there a speaker? Did you note any key connections made between attendees?
Students
Panelists
Defend Staff, Interns, Volunteers
Other
Lessons Learned | Next Steps
What worked well? What didn't? What should we do differently or the same next time? Record any key learnings here. | List any follow-ups, introductions to make, etc.